## Gantt Chart - Dependencies and
Gantt Chart Planning for Sprint 2
ID | Task name | Category | Assigned to | Start date | End date | Dependency (ID) | Dependency Type
1 | (Sprint 1 Continued) Manage GitHub pushes, merges and commits | Development | Karan | 2025-10-06 | 2025-10-07
1.1 | Verify branch strategy and PR workflow | Development | Karan | 2025-10-06 | 2025-10-06 | 1 | Start-to-Start
1.2 | Review & resolve PR conflicts / CI checks | Development | Karan | 2025-10-07 | 2025-10-07 | 1.1 | Finish-to-Start
2 | (Sprint 1 Continued) Research academic papers Part 1 (data evaluation) | Research | Priyanka | 2025-10-06 | 2025-10-08 | 1 | Start-to-Start
2.1 | Search & shortlist papers on accuracy/validation | Research | Priyanka | 2025-10-06 | 2025-10-07 | 2 | Start-to-Start
2.2 | Synthesize findings & extract key metrics | Documentation | Priyanka | 2025-10-07 | 2025-10-08 | 2.1 | Finish-to-Start
3 | (Sprint 1 Continued) Research academic papers Part 2 (AI-driven evaluation) | Research | Karan | 2025-10-07 | 2025-10-09 | 2 | Finish-to-Start
3.1 | Review ML-based evaluation techniques | Research | Karan | 2025-10-07 | 2025-10-08 | 3 | Start-to-Start
3.2 | Compare AI vs traditional evaluation approaches | Documentation | Karan | 2025-10-08 | 2025-10-09 | 3.1 | Finish-to-Start
4 | Evaluate APIs for routing/searching (OSM vs Mapbox) | Development | Karan | 2025-10-06 | 2025-10-09 | 1 | Finish-to-Start
4.1 | Benchmark OSM, Mapbox, Google (features/performance) | Research | Karan | 2025-10-06 | 2025-10-07 | 4 | Start-to-Start
4.2 | Assess cost & integration effort; recommend API | Analysis | Karan | 2025-10-07 | 2025-10-09 | 4.1 | Finish-to-Start
5 | Develop plan for data cleaning and preprocessing | Development | Hina | 2025-10-08 | 2025-10-10 | 4 | Finish-to-Start
5.1 | Define cleaning fields, rules, and edge cases | Development | Hina | 2025-10-08 | 2025-10-09 | 5 | Start-to-Start
5.2 | Draft step-by-step preprocessing workflow | Documentation | Hina | 2025-10-09 | 2025-10-10 | 5.1 | Finish-to-Start
6 | Create survey for pedestrians/cyclists | Research | Huda | 2025-10-06 | 2025-10-08
6.1 | Draft safety perception & routing questions | Research | Huda | 2025-10-06 | 2025-10-07 | 6 | Start-to-Start
6.2 | Pilot, refine, and finalize survey | Testing | Huda | 2025-10-07 | 2025-10-08 | 6.1 | Finish-to-Start
7 | Clean and organize GitHub repository | Development | Hina | 2025-10-09 | 2025-10-11 | 1 | Finish-to-Start
7.1 | Remove redundant branches & restructure | Maintenance | Hina | 2025-10-09 | 2025-10-10 | 7 | Start-to-Start
7.2 | Standardize folders & update README | Documentation | Hina | 2025-10-10 | 2025-10-11 | 7.1 | Finish-to-Start
8 | Create & schedule retrospective document | Management | Priyanka | 2025-10-06 | 2025-10-12
8.1 | Design template & reflection prompts | Documentation | Priyanka | 2025-10-06 | 2025-10-07 | 8 | Start-to-Start
8.2 | Schedule and assign reflections | Management | Priyanka | 2025-10-07 | 2025-10-12 | 8.1 | Finish-to-Start
9 | Enhance prototypes (medium-fidelity improvements) | Design | Huda | 2025-10-08 | 2025-10-12 | 6 | Finish-to-Start
9.1 | Refine UI flow and interaction sequence | Design | Huda | 2025-10-08 | 2025-10-10 | 9 | Start-to-Start
9.2 | Add hazard visualization & route comparison | Development | Huda | 2025-10-10 | 2025-10-12 | 9.1 | Finish-to-Start
9.3 | Conduct competitive analysis and integrate insights into prototype | Design | Huda | 2025-10-08 | 2025-10-11 | 9.2 | Start-to-Start
10 | Research environment setup (backend/frontend/tooling) | Development | Karan | 2025-10-06 | 2025-10-08 | 1 | Finish-to-Start
10.1 | Configure backend (Flask/Django) and DB | Development | Karan | 2025-10-06 | 2025-10-07 | 10 | Start-to-Start
10.2 | Validate frontend toolchain & API keys | Development | Karan | 2025-10-07 | 2025-10-08 | 10.1 | Finish-to-Start
11 | Create Gantt chart for the project | Management | Shalini | 2025-10-09 | 2025-10-10
11.1 | Map tasks, durations, and dependencies | Management | Shalini | 2025-10-09 | 2025-10-09 | 11 | Start-to-Start
11.2 | Review and finalize chart for upload | Management | Shalini | 2025-10-10 | 2025-10-10 | 11.1 | Finish-to-Finish
12 | Review previous projects (UX & routing case studies) | Research | Priyanka | 2025-10-10 | 2025-10-12 | 2 | Finish-to-Start
12.1 | Analyze case studies for performance insights | Research | Priyanka | 2025-10-10 | 2025-10-11 | 12 | Start-to-Start
12.2 | Summarize lessons for SafePath improvements | Analysis | Priyanka | 2025-10-11 | 2025-10-12 | 12.1 | Finish-to-Start
13 | Prepare weekly project presentation (Week 4) | Management | Shalini | 2025-10-06 | 2025-10-09
13.1 | Compile slides for Sprint 2 deliverables | Management | Shalini | 2025-10-06 | 2025-10-08 | 11 | Finish-to-Start
13.2 | Final rehearsal & speaker order confirmation | Communication | Shalini | 2025-10-09 | 2025-10-09 | 13.1 | Finish-to-Start
14 | Persona enhancement (refine based on survey data) | Design | Huda | 2025-10-09 | 2025-10-13 | 6 | Finish-to-Start
14.1 | Integrate survey insights into persona attributes | Research | Huda | 2025-10-09 | 2025-10-11 | 14 | Start-to-Start
14.2 | Update persona visuals and summaries | Design | Huda | 2025-10-11 | 2025-10-13 | 14.1 | Finish-to-Finish
15 | Update MOM logs for Week 4 | Documentation | Priyanka | 2025-10-06 | 2025-10-13 | 8 | Start-to-Start
15.1 | Summarize sprint discussions & decisions | Documentation | Priyanka | 2025-10-06 | 2025-10-12 | 15 | Start-to-Start
15.2 | Upload finalized MOM documents to GitHub | Maintenance | Priyanka | 2025-10-13 | 2025-10-13 | 15.1 | Finish-to-Finish