## Gantt Chart - Dependencies and
Sprint 2 Gantt Chart Planning and Decisions (6 Oct - 13 Oct)
Task ID | Task Name | Category | Assigned to | Start Date | End Date | Predecessors | Dependency ID | Dependency Type
1 | (Sprint 1 Continued) Manage GitHub pushes, merges and commits | Development | Karan | 2025-10-06 | 2025-10-07
1.1 | Verify branch strategy and PR workflow | Development | Karan | 2025-10-06 | 2025-10-06
1.2 | Review & resolve PR conflicts / CI checks | Development | Karan | 2025-10-07 | 2025-10-07 | 1.1FS | 1.1 | FS
2 | (Sprint 1 Continued) Research academic papers Part 1 (data evaluation) | Research | Priyanka | 2025-10-06 | 2025-10-08 | 1SS | 1 | SS
2.1 | Search & shortlist papers on accuracy/validation | Research | Priyanka | 2025-10-06 | 2025-10-07
2.2 | Synthesize findings & extract key metrics | Documentation | Priyanka | 2025-10-07 | 2025-10-08 | 2.1FS | 2.1 | FS
3 | (Sprint 1 Continued) Research academic papers Part 2 (AI-driven evaluation) | Research | Karan | 2025-10-07 | 2025-10-09 | 2FS | 2 | FS
3.1 | Review ML-based evaluation techniques | Research | Karan | 2025-10-07 | 2025-10-08
3.2 | Compare AI vs traditional evaluation approaches | Documentation | Karan | 2025-10-08 | 2025-10-09 | 3.1FS | 3.1 | FS
4 | Evaluate APIs for routing/searching (OSM vs Mapbox) | Development | Karan | 2025-10-06 | 2025-10-09 | 1FS | 1 | FS
4.1 | Benchmark OSM, Mapbox, Google (features/performance) | Research | Karan | 2025-10-06 | 2025-10-07
4.2 | Assess cost & integration effort; recommend API | Analysis | Karan | 2025-10-07 | 2025-10-09 | 4.1FS | 4.1 | FS
5 | Develop plan for data cleaning and preprocessing | Development | Hina | 2025-10-08 | 2025-10-10 | 4FS | 4 | FS
5.1 | Define cleaning fields, rules, and edge cases | Development | Hina | 2025-10-08 | 2025-10-09
5.2 | Draft step-by-step preprocessing workflow | Documentation | Hina | 2025-10-09 | 2025-10-10 | 5.1FS | 5.1 | FS
6 | Create survey for pedestrians/cyclists | Research | Huda | 2025-10-06 | 2025-10-08
6.1 | Draft safety perception & routing questions | Research | Huda | 2025-10-06 | 2025-10-07
6.2 | Pilot, refine, and finalize survey | Testing | Huda | 2025-10-07 | 2025-10-08 | 6.1FS | 6.1 | FS
7 | Clean and organize GitHub repository | Development | Hina | 2025-10-09 | 2025-10-11 | 1FS | 1 | FS
7.1 | Remove redundant branches & restructure | Maintenance | Hina | 2025-10-09 | 2025-10-10
7.2 | Standardize folders & update README | Documentation | Hina | 2025-10-10 | 2025-10-11 | 7.1FS | 7.1 | FS
8 | Create & schedule retrospective document | Management | Priyanka | 2025-10-06 | 2025-10-12
8.1 | Design template & reflection prompts | Documentation | Priyanka | 2025-10-06 | 2025-10-07
8.2 | Schedule and assign reflections | Management | Priyanka | 2025-10-07 | 2025-10-12 | 8.1FS | 8.1 | FS
9 | Enhance prototypes (medium-fidelity improvements) | Design | Huda | 2025-10-08 | 2025-10-12 | 6FS | 6 | FS
9.1 | Refine UI flow and interaction sequence | Design | Huda | 2025-10-08 | 2025-10-10
9.2 | Add hazard visualization & route comparison | Development | Huda | 2025-10-10 | 2025-10-12 | 9.1FS | 9.1 | FS
9.3 | Conduct competitive analysis and integrate insights into prototype | Design | Huda | 2025-10-08 | 2025-10-11 | 9.2SS | 9.2 | SS
10 | Research environment setup (backend/frontend/tooling) | Development | Karan | 2025-10-06 | 2025-10-08 | 1FS | 1 | FS
10.1 | Configure backend (Flask/Django) and DB | Development | Karan | 2025-10-06 | 2025-10-07
10.2 | Validate frontend toolchain & API keys | Development | Karan | 2025-10-07 | 2025-10-08 | 10.1FS | 10.1 | FS
11 | Create Gantt chart for Sprint 2 | Management | Shalini | 2025-10-09 | 2025-10-10
11.1 | Map tasks, durations, and dependencies | Management | Shalini | 2025-10-09 | 2025-10-09
11.2 | Review and finalize chart for upload | Management | Shalini | 2025-10-10 | 2025-10-10 | 11.1FF | 11.1 | FF
12 | Review previous projects (UX & routing case studies) | Research | Priyanka | 2025-10-10 | 2025-10-12 | 2FS | 2 | FS
12.1 | Analyze case studies for performance insights | Research | Priyanka | 2025-10-10 | 2025-10-11
12.2 | Summarize lessons for SafePath improvements | Analysis | Priyanka | 2025-10-11 | 2025-10-12 | 12.1FS | 12.1 | FS
13 | Prepare weekly project presentation (Week 4) | Management | Shalini | 2025-10-06 | 2025-10-09
13.1 | Compile slides for Sprint 2 deliverables | Management | Shalini | 2025-10-06 | 2025-10-08 | 11FS | 11 | FS
13.2 | Final rehearsal & speaker order confirmation | Communication | Shalini | 2025-10-09 | 2025-10-09 | 13.1FS | 13.1 | FS
14 | Persona enhancement (refine based on survey data) | Design | Huda | 2025-10-09 | 2025-10-13 | 6FS | 6 | FS
14.1 | Integrate survey insights into persona attributes | Research | Huda | 2025-10-09 | 2025-10-11
14.2 | Update persona visuals and summaries | Design | Huda | 2025-10-11 | 2025-10-13 | 14.1FF | 14.1 | FF
15 | Update MOM logs for Week 4 | Documentation | Priyanka | 2025-10-06 | 2025-10-13 | 8SS | 8 | SS
15.1 | Summarize sprint discussions & decisions | Documentation | Priyanka | 2025-10-06 | 2025-10-12
15.2 | Upload finalized MOM documents to GitHub | Maintenance | Priyanka | 2025-10-13 | 2025-10-13 | 15.1FF | 15.1 | FF
16 | Flow Chart: 'Search For Route' Requirement | Design | Priyanka | 2025-10-07 | 2025-10-08
16.1 | Draft Flow Chart | Design | Priyanka | 2025-10-07 | 2025-10-07
16.2 | Review & Finalize | Review | Priyanka | 2025-10-08 | 2025-10-08 | 16.1FS | 16.1 | FS
17 | Technical Architecture Confirmation | Architecture | Karan | 2025-10-07 | 2025-10-08
17.1 | Draft Architecture | Architecture | Karan | 2025-10-07 | 2025-10-07
17.2 | Team Review & Sign-Off | Review | Karan | 2025-10-08 | 2025-10-08 | 17.1FS | 17.1 | FS
18 | Website Application Development and Kickoff | Development | Karan | 2025-10-07 | 2025-10-08
18.1 | Project Scaffolding & Repository Setup | Development | Karan | 2025-10-07 | 2025-10-07
18.2 | Core Layout & Routing Skeleton | Development | Karan | 2025-10-07 | 2025-10-08 | 18.1FS | 18.1 | FS
18.3 | Initial Feature Stub - Search for Route | Development | Karan | 2025-10-08 | 2025-10-08 | 18.2FS | 18.2 | FS
19 | Weekly Videos Link | Communication | All | 2025-10-07 | 2025-10-08
19.1 | Record 1-Minute Video 1 | Communication | Shalini | 2025-10-07 | 2025-10-08
19.2 | Record 1-Minute Video 2 | Communication | Karan | 2025-10-07 | 2025-10-08
19.3 | Record 1-Minute Video 3 | Communication | Priyanka | 2025-10-07 | 2025-10-08
19.4 | Record 1-Minute Video 4 | Communication | Huda | 2025-10-07 | 2025-10-08
19.5 | Record 1-Minute Video 5 | Communication | Hina | 2025-10-07 | 2025-10-08
20 | Weekly Reflective Diary | Documentation | All | 2025-10-08 | 2025-10-13
20.1 | Weekly Diary Compilation 1 | Documentation | Shalini | 2025-10-08 | 2025-10-13
20.2 | Weekly Diary Compilation 2 | Documentation | Karan | 2025-10-08 | 2025-10-13
20.3 | Weekly Diary Compilation 3 | Documentation | Priyanka | 2025-10-08 | 2025-10-13
20.4 | Weekly Diary Compilation 4 | Documentation | Huda | 2025-10-08 | 2025-10-13
20.5 | Weekly Diary Compilation 5 | Documentation | Hina | 2025-10-08 | 2025-10-13